## Master Task List
Task ID | Phase | Category | Task Name | Description | Subtasks/Checklist | Assignee | Priority | Est. Hours | Dependencies | Status | Start Date | Due Date | Notes
PUSH-001 | 1 | Push Notifications | Set up Expo Push Notifications | Configure expo-notifications, request permissions, set up notification handlers | Install package, configure app.json, add permission request on startup |  | P0 | 4 |  | Not Started
PUSH-002 | 1 | Push Notifications | Create push_tokens table | Supabase table to store user device tokens for push notifications | CREATE TABLE with user_id, token, platform, created_at; Add RLS policies |  | P0 | 2 |  | Not Started
PUSH-003 | 1 | Push Notifications | Implement token registration | Register device token with Supabase on login/app launch | Get Expo push token, upsert to push_tokens table, handle token refresh |  | P0 | 3 | PUSH-001, PUSH-002 | Not Started
PUSH-004 | 1 | Push Notifications | Create notification Edge Function | Supabase Edge Function to send push notifications via Expo Push API | Accept user_id, title, body, data; Look up token; Call Expo Push API |  | P0 | 6 | PUSH-002 | Not Started
PUSH-005 | 1 | Push Notifications | Booking request notification | Trigger notification to host when new booking request received | Database trigger on bookings insert; Call Edge Function with host_id |  | P0 | 4 | PUSH-004 | Not Started
PUSH-006 | 1 | Push Notifications | Booking confirmation notification | Notify renter when host confirms booking | Database trigger on booking status change to CONFIRMED |  | P1 | 3 | PUSH-004 | Not Started
PUSH-007 | 1 | Push Notifications | New message notification | Notify user when they receive a new chat message | Database trigger on messages insert; Call Edge Function with recipient_id |  | P1 | 4 | PUSH-004 | Not Started
PUSH-008 | 1 | Push Notifications | Notification tap handling | Deep link to correct screen when user taps notification | Parse notification data.screen; Navigate to BookingDetail, Chat, etc. |  | P1 | 4 | PUSH-001 | Not Started
PUSH-009 | 1 | Push Notifications | Notification preferences | Allow users to enable/disable notification types in Profile | Add notification_preferences JSONB to profiles; Toggle UI in settings |  | P2 | 3 | PUSH-003 | Not Started
PUSH-010 | 1 | Push Notifications | Physical device testing | Test all notification types on real iPhone | Test booking, message, confirmation; Verify sound, badge, tap handling |  | P0 | 4 | PUSH-005, PUSH-006, PUSH-007, PUSH-008 | Not Started
PUSH-011 | 1 | Push Notifications | Permission handling | Gracefully handle denied permissions with explanation | Check permission status; Show explanation modal; Link to settings |  | P1 | 2 | PUSH-001 | Not Started
PUSH-012 | 1 | Push Notifications | Badge count management | Show unread message count on app icon | Track unread count; Update badge on new message; Clear on read |  | P2 | 2 | PUSH-007 | Not Started
PAY-001 | 2 | Payments | Stripe account setup | Create Stripe account, configure webhook endpoints | Create account; Enable test mode; Set up webhook URL; Note API keys |  | P0 | 2 |  | Not Started
PAY-002 | 2 | Payments | Create payment_methods table | Store user saved payment methods (tokenized) | user_id, stripe_payment_method_id, last4, brand, is_default, created_at |  | P0 | 2 |  | Not Started
PAY-003 | 2 | Payments | Create transactions table | Record all payment transactions | id, booking_id, user_id, amount, currency, status, stripe_payment_intent_id, type (charge/refund), created_at |  | P0 | 2 |  | Not Started
PAY-004 | 2 | Payments | Install Stripe React Native | Add @stripe/stripe-react-native and configure | npm install; Update app.json with merchantId; Initialize StripeProvider |  | P0 | 2 |  | Not Started
PAY-005 | 2 | Payments | Payment Intent Edge Function | Create Stripe PaymentIntent from Edge Function | Accept amount, customer_id; Create PaymentIntent; Return client_secret |  | P0 | 6 | PAY-001 | Not Started
PAY-006 | 2 | Payments | AddPaymentMethodScreen | UI for adding credit/debit card | CardField component; Save card; Handle errors; Show saved cards list |  | P0 | 6 | PAY-004 | Not Started
PAY-007 | 2 | Payments | Integrate payment in checkout | Add payment step to CheckoutScreen | Show saved cards; Add new card option; Confirm payment before booking |  | P0 | 8 | PAY-005, PAY-006 | Not Started
PAY-008 | 2 | Payments | Webhook handler | Process Stripe webhooks for payment events | Edge Function to handle payment_intent.succeeded, failed, refunded |  | P0 | 6 | PAY-001 | Not Started
PAY-009 | 2 | Payments | PaymentHistoryScreen | View past transactions in Profile | List transactions; Filter by type; Show status, amount, date |  | P1 | 4 | PAY-003 | Not Started
PAY-010 | 2 | Payments | Refund flow | Automatic refund when booking is cancelled | Check cancellation policy; Create Stripe refund; Update transaction record |  | P1 | 6 | PAY-008 | Not Started
PAY-011 | 2 | Payments | Payment method in Profile | Manage saved cards from Profile screen | View cards; Set default; Delete card; Add new card link |  | P1 | 3 | PAY-006 | Not Started
PAY-012 | 2 | Payments | Payment error handling | User-friendly error messages for all payment failures | Map Stripe error codes; Show retry option; Log errors |  | P0 | 4 | PAY-007 | Not Started
PAY-013 | 2 | Payments | Security deposit logic | Hold deposit, release after checkout | Capture vs authorize; Release on successful stay; Deduct for damages |  | P1 | 6 | PAY-005 | Not Started
PAY-014 | 2 | Payments | Host payout system | Pay hosts their earnings | Track host balance; Create payout; Handle payout failures |  | P1 | 8 | PAY-008 | Not Started
PAY-015 | 2 | Payments | Stripe Connect onboarding | Onboard hosts as Stripe Connected Accounts | Create connected account; Onboarding link; Handle verification |  | P1 | 8 | PAY-001 | Not Started
AUTH-001 | 3 | Social Auth | Apple Sign-In configuration | Configure in Apple Developer Portal | Enable Sign in with Apple; Add to App ID; Generate key |  | P0 | 2 |  | Not Started |  |  | Required for App Store
AUTH-002 | 3 | Social Auth | Google Sign-In configuration | Configure in Google Cloud Console | Create OAuth client; Add iOS bundle ID; Download config |  | P1 | 2 |  | Not Started
AUTH-003 | 3 | Social Auth | Enable Supabase providers | Enable Apple and Google in Supabase Auth | Add client IDs; Configure redirect URLs |  | P0 | 1 | AUTH-001, AUTH-002 | Not Started
AUTH-004 | 3 | Social Auth | Install expo-apple-authentication | Add Apple auth package | npm install; Configure plugin in app.json |  | P0 | 1 |  | Not Started
AUTH-005 | 3 | Social Auth | Install expo-auth-session | Add Google auth package | npm install; Configure scheme in app.json |  | P1 | 1 |  | Not Started
AUTH-006 | 3 | Social Auth | Apple Sign-In button - Login | Add Apple button to LoginScreen | AppleAuthentication.AppleAuthenticationButton; Handle response; Create session |  | P0 | 3 | AUTH-003, AUTH-004 | Not Started
AUTH-007 | 3 | Social Auth | Google Sign-In button - Login | Add Google button to LoginScreen | useAuthRequest hook; Handle response; Create session |  | P1 | 3 | AUTH-003, AUTH-005 | Not Started
AUTH-008 | 3 | Social Auth | Social auth profile creation | Create profile record for new social users | Check if profile exists; Create with name/email from provider; Handle avatar |  | P0 | 4 | AUTH-006, AUTH-007 | Not Started
AUTH-009 | 3 | Social Auth | Social buttons on SignUp | Add social options to SignUpScreen | Same buttons as login; Link to existing flow |  | P1 | 2 | AUTH-006, AUTH-007 | Not Started
AUTH-010 | 3 | Social Auth | End-to-end testing | Test complete social auth flows | Fresh account; Existing account; Error cases |  | P0 | 3 | AUTH-008 | Not Started
AUTH-011 | 3 | Social Auth | Account linking | Handle linking social to existing email account | Detect existing email; Prompt to link; Merge accounts |  | P2 | 3 | AUTH-008 | Not Started
AUTH-012 | 3 | Social Auth | Update auth store | Handle social provider sessions in Zustand | Store provider type; Handle token refresh; Logout cleanup |  | P0 | 2 | AUTH-006, AUTH-007 | Not Started
REV-001 | 4 | Reviews | Create reviews table | Supabase table for listing reviews | id, listing_id, reviewer_id, rating (1-5), title, content, created_at; Unique constraint on listing+reviewer |  | P0 | 2 |  | Not Started
REV-002 | 4 | Reviews | Reviews RLS policies | Secure access to reviews | Public read; Only reviewer can create own; Can't review own listing |  | P0 | 2 | REV-001 | Not Started
REV-003 | 4 | Reviews | Add rating to listings | Average rating field on listings table | ALTER TABLE listings ADD average_rating NUMERIC; Add review_count |  | P0 | 1 |  | Not Started
REV-004 | 4 | Reviews | Create reviewsApi.ts | API functions for reviews | createReview, getListingReviews, getUserReviews, updateAverageRating |  | P0 | 4 | REV-001 | Not Started
REV-005 | 4 | Reviews | WriteReviewScreen | UI for writing a review | Star rating input; Title; Content textarea; Submit button; Validation |  | P0 | 6 | REV-004 | Not Started
REV-006 | 4 | Reviews | Star rating component | Reusable star rating display/input | Display mode (read-only); Input mode (tappable); Half stars optional |  | P0 | 3 |  | Not Started
REV-007 | 4 | Reviews | Reviews on ListingDetail | Show reviews section on listing page | Average rating; Review count; List of reviews; Write review button |  | P0 | 4 | REV-004, REV-006 | Not Started
REV-008 | 4 | Reviews | Calculate average rating | Update listing rating when review added | Database trigger or Edge Function; Recalculate on insert/update/delete |  | P0 | 3 | REV-001, REV-003 | Not Started
REV-009 | 4 | Reviews | Review prompt after booking | Prompt user to review after stay completes | Check booking end_date; Show prompt in app; Link to WriteReviewScreen |  | P1 | 2 | REV-005 | Not Started
REV-010 | 4 | Reviews | My Reviews in Profile | View reviews user has written | List with listing info; Edit/delete options |  | P2 | 3 | REV-004 | Not Started
REV-011 | 4 | Reviews | Review reporting | Flag inappropriate reviews | Report button; Create reports table; Admin review queue |  | P2 | 3 | REV-001 | Not Started
REV-012 | 4 | Reviews | Host response to reviews | Allow hosts to respond to reviews | Add host_response column; Response UI on review; Display in listing |  | P2 | 4 | REV-007 | Not Started
ASSET-001 | 5 | App Store Assets | Design app icon | 1024x1024 app icon for App Store | Clean design; Recognizable at small sizes; No text; PNG format |  | P0 | 4 |  | Not Started |  |  | Designer task
ASSET-002 | 5 | App Store Assets | Generate icon sizes | All required iOS icon sizes | Use Expo or online tool; 20, 29, 40, 60, 76, 83.5, 1024 @1x, 2x, 3x |  | P0 | 1 | ASSET-001 | Not Started
ASSET-003 | 5 | App Store Assets | Design splash screen | Launch screen image | Match app icon style; Simple animation optional; All device sizes |  | P0 | 3 | ASSET-001 | Not Started
ASSET-004 | 5 | App Store Assets | 6.7 inch screenshots | iPhone 14 Pro Max / 15 Pro Max | 6 screens: Home, Map, Listing, Checkout, Messages, Profile; Add text overlays |  | P0 | 4 |  | Not Started |  |  | 1290 x 2796 px
ASSET-005 | 5 | App Store Assets | 6.5 inch screenshots | iPhone 11 Pro Max / XS Max | Same 6 screens scaled; Or use 6.7 and App Store will scale |  | P0 | 2 | ASSET-004 | Not Started |  |  | 1284 x 2778 px
ASSET-006 | 5 | App Store Assets | 5.5 inch screenshots | iPhone 8 Plus (optional but recommended) | Same 6 screens; Required if supporting older devices |  | P1 | 2 | ASSET-004 | Not Started |  |  | 1242 x 2208 px
ASSET-007 | 5 | App Store Assets | iPad screenshots | iPad Pro 12.9 inch (optional) | If app supports iPad; 6 screens at 2048 x 2732 |  | P2 | 3 | ASSET-004 | Not Started
ASSET-008 | 5 | App Store Assets | App Store description | Full description (4000 chars max) | Features list; How it works; Benefits; Call to action |  | P0 | 2 |  | Not Started
ASSET-009 | 5 | App Store Assets | Promotional text | Short promo (170 chars) | Catchy tagline; Can be updated without review |  | P0 | 1 |  | Not Started
ASSET-010 | 5 | App Store Assets | Keywords | Search keywords (100 chars) | Research competitors; Target user searches; No duplicates of name |  | P0 | 1 |  | Not Started
ASSET-011 | 5 | App Store Assets | Privacy Policy | Required privacy policy page | Data collected; How used; Third parties; User rights; Contact info |  | P0 | 3 |  | Not Started |  |  | Host on website
ASSET-012 | 5 | App Store Assets | Terms of Service | User agreement | User responsibilities; Prohibited content; Liability; Disputes |  | P0 | 3 |  | Not Started |  |  | Host on website
ASSET-013 | 5 | App Store Assets | Support URL/email | Customer support contact | Set up support email; Create FAQ page; Configure in App Store Connect |  | P0 | 1 |  | Not Started
ASSET-014 | 5 | App Store Assets | App preview video | 30-second preview (optional) | Screen recording with captions; Show key features; No hands |  | P2 | 6 |  | Not Started |  |  | Highly recommended
ASSET-015 | 5 | App Store Assets | Age rating questionnaire | Complete Apple age rating | Answer questions about content; Violence, mature themes, etc. |  | P0 | 1 |  | Not Started
BUILD-001 | 6 | Build Setup | Apple Developer account | Enroll in Apple Developer Program | $99/year; Verify identity; Wait for approval (24-48 hrs) |  | P0 | 1 |  | Not Started
BUILD-002 | 6 | Build Setup | App Store Connect listing | Create app in App Store Connect | Enter app name; Select bundle ID; Set primary language |  | P0 | 2 | BUILD-001 | Not Started
BUILD-003 | 6 | Build Setup | Certificates and profiles | Generate signing credentials | Distribution certificate; Provisioning profile; Push notification cert |  | P0 | 2 | BUILD-001 | Not Started
BUILD-004 | 6 | Build Setup | Install EAS CLI | Set up Expo Application Services | npm install -g eas-cli; eas login; eas build:configure |  | P0 | 1 |  | Not Started
BUILD-005 | 6 | Build Setup | Configure eas.json | Build profiles for dev, staging, production | Set build types; Environment variables; Credentials |  | P0 | 2 | BUILD-004 | Not Started
BUILD-006 | 6 | Build Setup | Production environment | Separate env vars for production | Supabase production URL; Stripe live keys; Sentry DSN |  | P0 | 2 |  | Not Started
BUILD-007 | 6 | Build Setup | Production Supabase project | Create separate production database | New Supabase project; Configure auth; Set up storage |  | P0 | 3 |  | Not Started
BUILD-008 | 6 | Build Setup | Migrate schema to prod | Apply all migrations to production DB | Run migrations; Verify tables; Test RLS policies |  | P0 | 2 | BUILD-007 | Not Started
BUILD-009 | 6 | Build Setup | Production Stripe keys | Switch to Stripe live mode | Get live API keys; Update Edge Functions; Test with real card |  | P0 | 1 | PAY-001 | Not Started
BUILD-010 | 6 | Build Setup | First production build | Run eas build --platform ios --profile production | Submit to EAS; Wait for build; Download IPA |  | P0 | 2 | BUILD-003, BUILD-005, BUILD-006 | Not Started
BUILD-011 | 6 | Build Setup | Fix build errors | Resolve any production build issues | Common: missing assets, plugin conflicts, native dependencies |  | P0 | 4 | BUILD-010 | Not Started
BUILD-012 | 6 | Build Setup | Test production build | Install and test on physical device | Install via TestFlight; Full regression test; Verify prod APIs |  | P0 | 3 | BUILD-010 | Not Started
BUILD-013 | 6 | Build Setup | Crash reporting (Sentry) | Set up error monitoring | Create Sentry project; Install sentry-expo; Configure source maps |  | P1 | 3 |  | Not Started
BUILD-014 | 6 | Build Setup | Analytics setup | User behavior tracking | Choose provider (Amplitude/Mixpanel); Install SDK; Track key events |  | P1 | 3 |  | Not Started
QA-001 | 7 | QA - Core | Auth flow testing | Complete auth feature testing | Login; Signup; Social auth; Session persistence; Logout; Password reset |  | P0 | 3 |  | Not Started
QA-002 | 7 | QA - Core | Home Screen testing | Complete home screen testing | Load listings; Filters; Pull-refresh; Empty state; Error state; Card interactions |  | P0 | 2 |  | Not Started
QA-003 | 7 | QA - Core | Map Screen testing | Complete map feature testing | Marker display; Info pills; Navigation; Location permissions |  | P0 | 2 |  | Not Started
QA-004 | 7 | QA - Core | Listing Detail testing | Complete listing detail testing | Image carousel; All fields display; Status badges; Owner vs visitor actions |  | P0 | 3 |  | Not Started
QA-005 | 7 | QA - Core | Checkout flow testing | Complete checkout feature testing | All 4 steps; Timer; Cancel; Success; Error handling; Payment |  | P0 | 4 |  | Not Started
QA-006 | 7 | QA - Core | Messaging testing | Complete messaging feature testing | Chat list; Send/receive; Real-time updates; Notifications |  | P0 | 3 |  | Not Started
QA-007 | 7 | QA - Core | Profile testing | Complete profile feature testing | User info; My listings; Saved; Edit; Logout; Payment methods |  | P0 | 2 |  | Not Started
QA-008 | 7 | QA - Core | Post Listing testing | Complete post listing testing | All 4 wizard steps; Validation; Image upload; Edit mode |  | P0 | 3 |  | Not Started
QA-009 | 7 | QA - Features | Push notifications E2E | Test all notification types | Token registration; Booking alerts; Message alerts; Tap handling; Badge |  | P0 | 3 | PUSH-010 | Not Started
QA-010 | 7 | QA - Features | Payment flow E2E | Test complete payment flow | Add card; Charge; Success; Failure; Webhook handling; Refund |  | P0 | 4 | PAY-012 | Not Started
QA-011 | 7 | QA - Features | Social auth E2E | Test social login flows | Apple Sign-In; Google Sign-In; Profile creation; Account linking |  | P0 | 2 | AUTH-010 | Not Started
QA-012 | 7 | QA - Features | Reviews flow E2E | Test review functionality | Write review; Star rating; Display; Average calculation; Report |  | P0 | 2 | REV-008 | Not Started
QA-013 | 7 | QA - Security | SQL injection testing | Test input sanitization | All text inputs; Search; Filters; Verify RLS blocks malicious queries |  | P0 | 2 |  | Not Started
QA-014 | 7 | QA - Security | XSS prevention testing | Test output encoding | Description; Messages; Reviews; Verify HTML/JS not executed |  | P0 | 2 |  | Not Started
QA-015 | 7 | QA - Security | Auth bypass testing | Test authentication security | Direct API calls; Expired tokens; Role escalation attempts |  | P0 | 2 |  | Not Started
QA-016 | 7 | QA - Security | RLS policy verification | Verify row-level security | Cross-user data access attempts on all tables; Verify denials |  | P0 | 3 |  | Not Started
QA-017 | 7 | QA - Security | Sensitive data exposure | Check for data leaks | Logs; Error messages; API responses; No passwords/tokens exposed |  | P1 | 2 |  | Not Started
QA-018 | 7 | QA - Payment | Declined card scenarios | Test payment failures | Insufficient funds (4000000000009995); Expired; Invalid CVV |  | P0 | 2 | PAY-012 | Not Started |  |  | Stripe test cards
QA-019 | 7 | QA - Payment | 3D Secure flow | Test 3DS authentication | Use 3DS test card; Complete challenge; Fail challenge |  | P0 | 2 | PAY-012 | Not Started
QA-020 | 7 | QA - Payment | Refund testing | Test refund scenarios | Cancel booking refund; Verify transaction record; Check Stripe dashboard |  | P0 | 2 | PAY-010 | Not Started
QA-021 | 7 | QA - Payment | Webhook failure handling | Test webhook resilience | Retry logic; Idempotency; Manual reconciliation |  | P1 | 2 | PAY-008 | Not Started
QA-022 | 7 | QA - Payment | Payment timeout | Test network issues during payment | Kill network mid-payment; Verify state; Recovery flow |  | P1 | 1 | PAY-012 | Not Started
QA-023 | 7 | QA - Performance | App launch time | Measure cold start performance | Target: < 3 seconds; Profile with Xcode; Optimize if needed |  | P1 | 2 |  | Not Started
QA-024 | 7 | QA - Performance | Screen load times | Measure navigation performance | Target: < 1 second for all screens; Check API response times |  | P1 | 2 |  | Not Started
QA-025 | 7 | QA - Performance | Image loading | Test image performance | Lazy loading; Caching; Placeholder images; Large image handling |  | P1 | 2 |  | Not Started
QA-026 | 7 | QA - Performance | Memory profiling | Check for memory leaks | 10 min usage; Navigate all screens; Check Xcode memory graph |  | P1 | 2 |  | Not Started
QA-027 | 7 | QA - Performance | Battery impact | Test battery usage | Background activity; Location usage; Push notification impact |  | P2 | 1 |  | Not Started
QA-028 | 7 | QA - Platform | TestFlight internal | Internal team testing | Distribute to team; Collect feedback; Track bugs in issues |  | P0 | 3 | BUILD-012 | Not Started
QA-029 | 7 | QA - Platform | TestFlight external beta | External beta testing | 10-20 external testers; 1 week testing; Collect feedback |  | P0 | 4 | QA-028 | Not Started
QA-030 | 7 | QA - Platform | Multi-device testing | Test on various iPhones | iPhone SE (small); iPhone 14 (medium); iPhone 15 Pro Max (large) |  | P0 | 3 |  | Not Started
SUB-001 | 8 | Submission | Upload final build | Submit build to App Store Connect | eas submit --platform ios; Wait for processing |  | P0 | 1 | BUILD-010 | Not Started
SUB-002 | 8 | Submission | App information | Fill out all App Store Connect fields | Category; Copyright; Support info; Content rights |  | P0 | 2 |  | Not Started
SUB-003 | 8 | Submission | Upload screenshots | Add all screenshot sizes | Upload 6.7, 6.5, 5.5 inch sets; Add preview video if available |  | P0 | 1 | ASSET-004, ASSET-005, ASSET-006 | Not Started
SUB-004 | 8 | Submission | Privacy policy URL | Link privacy policy in listing | Must be publicly accessible HTTPS URL |  | P0 | 1 | ASSET-011 | Not Started
SUB-005 | 8 | Submission | App Review questionnaire | Complete Apple review questions | Content descriptions; Age rating; Encryption usage |  | P0 | 1 |  | Not Started
SUB-006 | 8 | Submission | Demo account | Create test account for reviewers | Email: demo@room-app.com; Password: [secure]; Pre-populate data |  | P0 | 1 |  | Not Started
SUB-007 | 8 | Submission | Submit for review | Click Submit for Review button | Double-check all info; Submit; Wait 24-48 hours |  | P0 | 1 | SUB-001 through SUB-006 | Not Started
SUB-008 | 8 | Submission | Review feedback response | Handle rejection or questions | Check Resolution Center; Respond to reviewer; Clarify if needed |  | P0 | 4 | SUB-007 | Not Started |  |  | If rejected
SUB-009 | 8 | Submission | Address review issues | Fix any problems Apple identifies | Code changes; Metadata updates; Policy compliance |  | P0 | 8 | SUB-008 | Not Started |  |  | If rejected
SUB-010 | 8 | Submission | Resubmit if needed | Submit fixed version | Upload new build; Reply to resolution; Resubmit |  | P0 | 1 | SUB-009 | Not Started |  |  | If rejected
SUB-011 | 8 | Submission | Set release date | Choose when app goes live | Immediate; Specific date; Manual release |  | P0 | 1 | SUB-007 | Not Started
SUB-012 | 8 | Submission | Release to App Store | Make app publicly available | Click Release This Version; Verify on App Store |  | P0 | 1 | SUB-011 | Not Started

## Phase Summary
Phase | Name | Tasks | Est. Hours | Duration | Dependencies | Key Deliverables
1 | Push Notifications | 12 | 40 | Week 1-2 | None | Expo Push setup, booking/message alerts, deep linking
2 | Payment Integration | 15 | 60 | Week 2-4 | None (parallel) | Stripe integration, checkout payment, host payouts
3 | Social Authentication | 12 | 24 | Week 4-5 | None (parallel) | Apple Sign-In (required), Google Sign-In
4 | Reviews & Ratings | 12 | 35 | Week 5-6 | None (parallel) | Review system, star ratings, averages
5 | App Store Assets | 15 | 30 | Week 6-7 | Phases 1-4 | Icons, screenshots, descriptions, legal docs
6 | Production Build | 14 | 25 | Week 7-8 | Phase 5 | Apple Developer, EAS Build, production environment
7 | Testing & QA | 30 | 55 | Week 8-9 | Phase 6 | Full regression, security, performance, beta testing
8 | App Store Submission | 12 | 15 | Week 9-10 | Phase 7 | Submit, review, release
TOTAL |  | 122 | 285 | 10 weeks

## Team Assignment
Engineer | Primary Track | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6 | Phase 7 | Phase 8
Engineer 1 | Push Notifications Lead | Phase 1: PUSH-001 to PUSH-006; Phase 7: QA-009
Engineer 2 | Push Notifications | Phase 1: PUSH-007 to PUSH-012
Engineer 3 | Payments Lead | Phase 2: PAY-001 to PAY-008; Phase 7: QA-010, QA-018-22
Engineer 4 | Payments | Phase 2: PAY-009 to PAY-015
Engineer 5 | Auth Lead | Phase 3: AUTH-001 to AUTH-008; Phase 7: QA-011, QA-013-17
Engineer 6 | Auth + Reviews | Phase 3: AUTH-009 to AUTH-012; Phase 4: REV-001 to REV-006
Engineer 7 | Reviews Lead | Phase 4: REV-007 to REV-012; Phase 7: QA-012
Engineer 8 | Assets Lead | Phase 5: ASSET-001 to ASSET-010
Engineer 9 | Assets + Legal | Phase 5: ASSET-011 to ASSET-015
Engineer 10 | Build Lead | Phase 6: BUILD-001 to BUILD-009; Phase 8: SUB-001 to SUB-007
Engineer 11 | Build + DevOps | Phase 6: BUILD-010 to BUILD-014; Phase 8: SUB-008 to SUB-012
Engineer 12 | QA Lead | Phase 7: QA-001 to QA-008, QA-023-30

## Timeline
Phase / Week | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
1. Push Notifications | bar: Week 1 to Week 2
2. Payments | bar: Week 2 to Week 4
3. Social Auth | bar: Week 4 to Week 5
4. Reviews | bar: Week 5 to Week 6
5. App Store Assets | bar: Week 6 to Week 7
6. Build Setup | bar: Week 7 to Week 8
7. Testing & QA | bar: Week 8 to Week 9
8. Submission | bar: Week 9 to Week 10